## ADKAR Assessment
Stakeholder Group | Awareness | Desire | Knowledge | Ability | Reinforcement | Key Risk | Mitigation Action | Delivery Implication
Agents | Daily operations friction caused by duplicate calls, and data scattered in multiple sources. | A centralised data source, customer contact information and history accessibility, and some agency given to customers. | Low: Agents are not able to understand customer contact history immediately due to scattered data. | Agents to be trained on the new system, pending Phase 1 delivery. | New system must be intuitive and efficient enough for agents to continue using it at the efficiency rates predicted. This can be measured through interval feedbacks from agents on the new platform during phase 1. These intervals could be weekly initially and drop off as issues get fixed overtime on phase 1 | Automations may remove some context that agents typically had before. This could include customer contact history that has a risk of being completely deferred to automation processes. | Communicate with senior team leaders, and retain backups of the old system for quick retrieval during phase 1 debugging. | These should be recorded as backlog items that can be worked on continuously throughout phase 1 to ensure agent workflows are as efficient as predictions by the end of phase 1. This will involve iteration cycles in the form of 1 week sprints.
Team leaders and managers | Teams struggles with scale as well as the system's weaknesses. | As-Is process mapped accurately, as well as a To-Be workflow that clearly details where agent work ends and begins. | Medium: As-Is process is mapped out now, and the To-Be is proposed but not fully complete. | Access to new centralised database. TBD pending Phase 1 delivery. | New data source must be complete and convenient enough for team leaders to continually use over scattered sources like emails and standalone spreadsheets. | Incomplete data migration to the new centralised source and unclear escalation pathways. | Continuous improvement on database source collection, governance to assess current data source completeness. | Automated escalation is out of the scope of phase 1, because this will take away from development time of the core functionality of the new portal.
Operations leadership | Daily strains on teams, where agents keep checking if someone has already called, and reconciling multiple sources. Promise tracking is also heavily manual. | Visualising where current process break, which automations are most effective and realistic future workflows of agents. | Medium: Similar to team leaders as they have a visualisation of current processes, but to-be-flows not ready yet. | Access to new centralised database. TBD pending Phase 1 delivery. | Efficiency changes must be consistent across phase 1 in order for leadership to continue developing on the project. | Incomplete data migration to the new centralised source. | Continuous improvement on database source collection, governance to assess current data source completeness. | Leadership will want to see transparent and consistent data in the new centralised source as well as quantifiable efficiency gains in agent workflows, such as calls-per-agent, duplicate contact rate and time-to-resolution falling.
Finance | 15% revenue loss due to delayed actions and inconsistent follow-ups. | Automations that create measurable savings and improve collections. As well as which assumptions are required. | Medium: ROI figures and calculations based on evidence and assumptions provided but not concrete due to presence of assumptions. Confidence will increase once phase 1 gathers enough data. | Retrieve financial data, which depends on outcomes of phase 1 at least. | Time savings must be consistently efficient to justify the automation opportunities that do not have a positive base case ROI (All opportunities have positive ROI when accounting for revenue uplift). | Assumptions not holding up in either production or scale. | Sensitivity analysis can mitigate unknown outcomes by providing a range based on scenarios. | Sensitivity analysis in discovery phase should see the true outcomes of phase 1 within its boundaries due to the careful boundaries set in the sensitivity analysis.
Product and delivery | First project and highly vigilant. Wants to ensure the discovery is infallible and allows a backlog. | Fully documented and traceable assessment that maps pain point -> opportunity -> workflow -> requirement. | High: Regular, up-to-date, and consistent access to documentation of the project. | Trained to use deliverables from this project, such as a dashboard of current statistics as well as forecasted results. Will be more informative after phase 1. | Phase 1 outputs must be consistently well-documented to ensure project success. | Untraceable documents. | A complete and up-to-date traceability matrix that links pain points to backlog items. | Dependencies of core functionality such as identity verification and account summary views must be prioritised first within phase 1 even though they are not direct automation opportunities.