## Sheet1
Deliverable | Time to Complete | Potential Blockers | Justification
1. Phase 1 Scope Definition | 2–3 hours (Completion: Day 1) | Stakeholder pushback on deferring features (e.g., Gareth wanting full promise-to-pay auto-escalation or Daniel questioning ROI). | Scope must be locked first so that downstream backlog items and UI wireframes are strictly bounded to Phase 1.
2. To-Be Workflow (Camunda) | 2-3 hours (Completion: Day 2) | Unclear exception paths for cases that need agent escalation | Visualisation of workflows allows for a high-level overview for understanding the ideal output of phase 1
3. Product Jira Backlog & Acceptance Criteria | 5–7 hours (Completion: Day 2–3) | Translating JTBDs (SN-001, SN-002, SN-037, SN-038) into INVEST-compliant user stories and writing edge cases in Given-When-Then format. | Highest complexity item; requires translating system capabilities into precise, developer-ready user stories and testable acceptance criteria.
4. Prototyping the portal | 4–5 hours (Completion: Day 3–4) | GenAI code can easily implement out-of-scope elements unprompted due to its non-deterministic nature. Ensuring this does not happen for phase 1 is critical | Replacing static wireframes with a working, functional prototype shows Amina and Gareth tangible proof of how straightforward cases self-serve without creating messy handoffs
5. Executive Briefing Storyboard | 3–4 hours (Completion: Day 4) | Synthesizing complex ROI data, addressing the 38% sample data caveat, and balancing competing stakeholder priorities succinctly. | Demands the highest level of polish; depends on all previous deliverables (Scope, Backlog, Protoypes) to build a cohesive narrative.